Possible timeline for next Letter Ballots

The following table provides a possible timeline for the upcoming Letter Ballots for the 802.11 standard.

| Week id by Monday | Activity | Event | Remarks |
| --- | --- | --- | --- |
| August 28 | Interim meeting Schaumburg |  |  |
| September 4 |  |  |  |
| September 11 |  | D2.0 LB closes September 14 |  |
| September 18 | Consolidation of result (Vic) |  |  |
| September 25 | Consolidation of result (Vic) | D2.0 LB result on server on September 28 |  |
| October 2 |  | Second mailing Oct 6 |  |
| October 9 |  |  |  |
| October 16 |  |  |  |
| October 23 |  |  |  |
| October 30 |  |  |  |
| November 6 | Plenary meeting Montreal PQB |  |  |
| November 13 | Prepare D2.1 (editors) |  |  |
| November 20 | Prepare D2.1 (editors) |  |  |
| November 27 | Repro and mailing | D2.1 LB starts December 1 Available on server Nov 27 | This is a WG confirmation ballot |
| December 4 |  |  |  |
| December 11 |  |  |  |
| December 18 |  |  |  |
| December 25 |  |  |  |
| January 1 | Consolidation of results (Vic) | D2.1 LB closes December 31 | 30 days from putting on the carrier |
| January 8 | Interim meeting |  |  |
| January 15 | Prepare D2.2 (editors) available Jan 19 for Vic |  |  |
| January 22 | Distribution by IEEE | D2.2 and D3.0 on server January 23 mailed January 26 | This is the Sponsor Group LB |
| January 29 |  |  |  |
| February 5 |  |  |  |
| February 12 |  |  |  |
| February 19 |  |  |  |
| February 26 |  |  |  |
| March 4 |  | Ballot closes March 3 | 40 days from server 36 days from mailing date |
| March 11 | Plenary meeting La Jolla | Result available March 9 | Start on Sunday or Saturday? |
| March 18 | Editors prepare D3.1 |  | D3.1 in Vic’s office Mar 22 |
| March 25 |  | D3.1 on server March 25 mailed March 29 | This is the Sponsor Group Confirmation LB |
| April 1 |  |  |  |
| April 8 |  |  |  |
| April 15 |  |  |  |
| April 22 | Distribution by IEEE | Ballot closes April 24 | 30 days from server 26 days from mailing date |
| April 29 |  |  |  |
| May 6 |  |  | May 10 deadline for Draft in paper at IEEE office for Standards Board |
| May 13 | Interim meeting (TBD) |  |  |
| May 20 |  |  |  |
| May 27 |  |  |  |
| June 3 |  |  |  |
| June 10 |  |  |  |
| June 17 |  |  |  |
| June 24 |  |  |  |
| July 1 |  |  |  |
| July 8 |  |  |  |
| July 15 | Plenary meeting in the Netherlands |  |  |
| July 22 |  |  |  |
| July 29 |  |  |  |
| August 5 |  |  | August 9 Deadline for Darft in paper to be in the IEEE office for Standards Board |
| August 12 |  |  |  |
| August 19 |  |  |  |