## IEEE-Cover
November 2000 |  | IEEE P802.15.3-00/354r1
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | P802-15_TG3-Draft-Open-Issues-List
Date Submitted | [Sept, 2001]
Source | [Bill Shvodian] | Voice: [(703)-269-3047]
| XtremeSpectrum, Inc. | Fax: [ ]
| [8133 Leesburg Pike] | E-mail: [bshvodian@xtremespectrum.com ]
[ Vienna, VA 22182 ]
Re: | 00000d06P802-15-3_Draft-Standard.pdf
Abstract
Purpose | [This document provides a home for all comments, open issues and suggested resolutions concerning the TG3 00000d06P802-15-3_Draft-Standard.pdf. In addition, this document will keep a running status of the disposition of the suggested resolutions.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Score Sheet
Withdrawn | Z | 2
Open | O | 128
Written | W | 2
Closed | C | 59
Unsatisfied | U | 0
Problem Class | Priority | Class Total
DesMode | 0 | 2
Scan | 1 | 2
Spelling | 1 | 3
Start | 1 | 3
Synch | 1 | 3
Table | 1 | 3
CTA | 1 | 4
Frame Format | 1 | 4
Frame Length | 1 | 4
Grammar | 1 | 35
Repeater | 2 | 2
TPC | 2 | 3
Channel Status Response | 2 | 4
Channel Time Request | 2 | 5
CoordHndOvr | 2 | 5
CFP | 2 | 6
CoordSel | 2 | 8
SEC | 3 | 3
PwrMgt | 3 | 4
CAP | 3 | 4
Auth | 3 | 9
Assoc | 3 | 14
Stream Mgt | 3 | 16

## OI-List-Srtd
| Color Codes |  |  |  |  | W | Changes approved | This Sheet uses autoformat for cell colors except for closed. (Excel only handles 3 conditional formats)
|  | C | Closed |  |  | A | Assigned
|  | P | Proposal pending |  |  | O | Open, not assigned | Last Issue Number | 398
Issue Number | Commenter's Initials | Draft Version Number | Clause number e.g., 8.10.2 | Page number e.g., 1-1130, etc. | Line number e.g., 1-54 | Type of comments (E/e/T/t) | Class of Problem | Comment/Rationale (Issue and reasoning behind it.) | Recommended change (What change(s) it would take to make this clause acceptable.) | Disposition/Rebuttal (Do not write here during ballot phase; this is for comment resolution phase.) | Issue Status X,D,Q,A,R | Resolution Status O,W,C,U,Z | Date Entered | Date Completed | Asignee |  | Issue Status | Resolution Status
315 | ADH | 6 | 8.1 | 95 | 39 | E | Grammar | The operation and the negotiations required for such transmit power... | Delete the word "such" from the indicated sentence fragment. |  | X | O
244 | ADH | 6 | 7.2.1.1.2 | 67 | 2 | E | ACK | … according toe … | replace toe with to |  | X | O
69 | ADH | 6 | 7.5.2 | 56 | 49 | T | Assoc | Authentication Process needs to be defined before we have a valid association policy. | Please Define. | Auth. Policy is being investigated. | X | A |  |  | Rasor
375 | ADH | 6 | 6.3.6.1 | 29 | 14-15 | E | Assoc | Missing cross reference | Please add cross reference pointing to clause 7.4.3 the Capability Info Element |  | X | O
376 | ADH | 6 | 6.3.6.1 | 29 | 17-18 | T | Assoc | AllocatedDevice Address is not known by the requesting DEV. Consequently, why include it. | Please Delete the Allocated Device Address table entries from the table. |  | X | O
374 | ADH | 6 | 6.3.6.1 | 29 | 2 | T | Assoc | AllocatedDevice Address is not known by the requesting DEV. Consequently, why include it. | Delete the Allocated Device Address from the MLME-Associate.req parm list. |  | X | O
379 | ADH | 6 | 6.3.6.2 | 29 | 37-40 | T | Assoc | Clause 6.3.6.2 describes the MLME primitive that is generated when an assoc.rsp message is received by a DEV whose Device-ID is specified in the parm field of assoc.rsp. While, Clause 8.2.5 ,p98, line16-17, describes how assoc.rsp is a broadcast frametype which DEVs in the piconet may receive and use the info contained there in to add to their association table a newly associated DEV's Device-ID/AD-AD. The issue is there currently is not defined an MLME primitive that will pass the appropriate information from the Assoc.rsp upto the SME. Consequently, there is need for an MLME-xxxx.indication containing these parameters: Device-ID, AD-AD | Please add MLME-xxxx.indication(Device-ID, AD-AD). Also add a parameter table for this primitive describing Device-ID and AD-AD) |  | X | O
377 | ADH | 6 | 6.3.6.2 | 29 | 39-41 | T | Assoc | These parameters are missing from the MLME-ASSOCIATE.confirm primitive: Device-ID, AllocatedDeviceAddress, ATP. Also change ResultCode to ReasonCode | Please add the new parameters and change ResultCode to ReasonCode. The order of these parameters shall be Device-ID, ReasonCode, AD-AD, ATP. |  | X | O
378 | ADH | 6 | 6.3.6.2 | 29 | 47-54 | T | Assoc | Table 16 is missing these parameters: Device-ID, AllocatedDeviceAddress, ATP. Also change ResultCode to ReasonCode | Add the missing parameters to the table and these definitions for the various fields in the table: ReasonCode; AllocatedDeviceAddress Type: 1 Octet, Valid Range: 0x00-0xFF, Description: The address allocated to the requesting device by the PNC; Association Timeout Period(ATP) Type: 2 Octets, Description: ATP that the PNC supports. |  | X | O
380 | ADH | 6 | 6.3.6.3 | 30 | 16-18 | T | Assoc | MLME-ASSOCIATE.indication is missing these parameters: Capability info element, AssociationTimeoutPeriod(ATP) | Please add the missing parameters. |  | X | O
381 | ADH | 6 | 6.3.6.3 | 30 | 25-26 | T | Assoc | MLME-ASSOCIATE.indication table is missing these parameters: Capability info element, AssociationTimeoutPeriod(ATP) | Please add missing parameters to table and reference appropriate sections of document. |  | X | O
277 | ADH | 6 | 7.5.2 | 81 | 16 | T | Assoc | …that is described in TBD | Please provide TBD reference or definition |  | X | O
278 | ADH | 6 | 7.5.3 | 81 | 31 | T | Assoc | The structure of the assoc. rsp frame body is the same as for the assoc. request command… This sentence is incorrect. The assoc. req does not indicate a reason code field. Therefore there is a need a separate figure for assoc. | This sentence is incorrect. The assoc. req does not indicate a reason code field. Need a separate figure for assoc. |  | X | O
316 | ADH | 6 | 8.2 | 96 | 1-2 | T | Assoc | … The DEV shall not start a new piconet in a channel if it detects an active 802.15.3 piconet in the same channel. Comment: So what is the DEV going to do if there are no open channels? Does it pass a parameter to the MLME.Start.confirm to indicate "unable to start piconet"? | Provide more detail regarding the results of not having a clear channel and by referencing the MLME-Start.confirm clause which needs to include an additional reason code. |  | X | O
323 | ADH | 6 | 8.2.5 | 97 | 52 | T | Assoc | When the PNC receives a valid association… | Please define what is a valid association request |  | X | O
328 | ADH | 6 | 8.2.5 | 98 | 24-25 | T | Assoc | …as illustrated in a Figure 46. The message sequence chart for the same is shown in Figure 47. These two referenced figures are redundant. | Modify Figure 47 to capture the info illustrated in Figure 46 and then remove figure 46 . |  | X | O
72 | WMS | 6 | 7.5.2 | 81 |  |  | Assoc. | What is the purpose of the Association Timeout period? | Describe how it is used or remove | ATP is the heartbeat of the piconet | D | A |  |  | Akahane | Proposal due 9/17/01 | Dependent upon PwrSave resolution
75 | WMS | 6 | 7.5.3 | 82 |  |  | Assoc. | What is the purpose of the Association Timeout period? | Describe how it is used or remove | ATP is the heartbeat of the piconet | D | A |  |  | Akahane | Proposal due 9/17/01
76 | WMS | 6 | 7.5.2, 7.5.3 |  |  |  | Assoc. | Remove Challenge Test from Association Request and Response. |  | Auth. Policy is being investigated. | X | A |  |  | Rasor
27 | ADH | 6 | 6.3.4.1 | 21 | 18 | T | Auth | Until we define an Authentication Policy there is no point in defining an MLME-Authenticate.request signal and its parameters. | Please Remove. | Auth. Policy is being investigated. | X | A |  |  | Rasor
28 | ADH | 6 | 6.3.4.2 | 22 | 6 | T | Auth | Until we define an Authentication Policy there is no point in defining an MLME-Authenticate.confirm signal and its parameters. | Please Remove. | Auth. Policy is being investigated. | X | A |  |  | Rasor
41 | ADH | 6 | 7.5 | 49 | 30 | T | Auth | When we define an Authentication Policy, we will need to add an Authentication frame type to this table. |  | Auth. Policy is being investigated. | X | A |  |  | Rasor
70 | ADH | 6 | 7.5.2 | 56 | 25 | t | Auth | Isn't this better suited for inclusion in an authentication frame type? |  | Auth. Policy is being investigated. | X | A |  |  | Rasor
101 | ADH | 6 | 7.4.7 | 64 | 1 | T | Auth | Security Parms are TBD. | Please identify security parms. | Auth. And Privacy Policy is being investigated. | X | A |  |  | Rasor
26 | RDR | 6 | 6.3.4 | 21 | 14-54 | T | Auth | Authentication Process needs to be defined. Currently, TBD. | Please Define. | Auth. Policy is being investigated. | X | A |  |  | Rasor
29 | ADH | 6 | 6.3.4.3 | 23 | 1 | T | Auth | Until we define an Authentication Policy there is no point in defining an MLME-Authenticate.indication signal and its parameters. | Please Remove. | Auth. Policy is being investigated. | X | A |  |  | Rasor
30 | ADH | 6 | 6.3.5 | 23 | 35 | T | Auth | Until we define an Authentication Policy there is no point in defining MLME-DeAuthenticate.xxx signals and their parameters. | Please Remove. | Auth. Policy is being investigated. | X | A |  |  | Rasor |  |  | x
31 | RDR | 6 | 6.3.5 | 23 | 35 | T | Auth | De-Authenticate Policy is undefined in 802.15.3 | Please Remove. | Auth. Policy is being investigated. | X | A |  |  | Rasor |  |  | x
169 | EdNote | 2 | 8.4 | 92 | 31 | t | CAP | When does stream negotiation occur? During CAP or CFP? | I recommend during MTS(Management Time Slots) | Devices can transmit data frames during the CAP if it has no appropriate GTS slots. See table 46 section 8.13 in 293r1 | A | A |  |  | Shvodian | Proposal due from B. Shvodian, due 09/17/01 | See R.Gubbi | x
338 | WMS | 6 | 8.3.2 | 102 |  | T | CAP | Need to bound Data frame size and frame throughput in CAP.
260 | ADH | 6 | 7.4.2 | 74 | 37 | E | CAP | When a DEV sends this element in one of its frames, for all the fields, it sends the same… | Please clarify what frames this element can be sent in. Please clarify …for all fields… |  | X | O
222 | Vienna | 4 |  |  |  | T | CAP | Can data be sent during the CAP? Don't want stations to have to listen to the CAP. | Bill will add text into 01259 Need to address all sections of Draft |  | D | A |  |  | Shvodian | Proposal due from B. Shvodian, due 09/17/01 | Separate item proposal
397 | WMS | 7 | 7.4.3 | 75 | 22-28 | T | Capability Field | RTC should be removed. It is no longer used. | Remove RTC from here and acronyms. Replace with PSave. Add PSrc. Update all sections to reflect this. Make sure they are not duplicated. Put into comparison order with high priority is msb. Make sure 1 is desired so that greater than would be comparison. msb- AC, PNC-Des-Mode, SEC, PSrc, PSave, Supported data rates, ten reserved. |  | X | W |  |  | Gilb
344 | ADH | 6 | 8.3.3 | 103 | 11-12 | T | CFP | … Hence, if a DEV did not correctly receive the beacon, that DEV is not allowed to access the channel during the CFP. Why not? I thought a DEV with assigned GTSs was allowed to transmit during its assigned GTSs for at least x number of contigously missed beacons. | Please clarify which is the correct policy. The current one stated in this clause or the one I thought was in effect. |  | X | O |  |  |  | B. Shvodian to add text to static GTS slots
349 | ADH | 6 | 8.3.3.2 | 104 | 1 | T | CFP | … If a DEV did not receive the CTA information, it shall not access the channel… Comment: Seems there is need for more specific text here. For instance, did the device miss the first beacon after it requested channel time, in which case the policy is correct. Or did it hear its GTS assignments from a previous beacon and not the one it was expecting? Consequently, it seems rather draconian that the DEV is not allowed to transmit during its last known good GTS assignment. | Please add text to clarify the GTS transmission policy. |  | X | O |  |  |  | B. Shvodian to add text to static GTS slots
350 | ADH | 6 | 8.3.3.2 | 104 | 19-27 | T | CFP | This paragraph referenced here is dependent upon there being a channel time request rejection indication which does not exist. For instance, there is nothing in the CTA info elements to indicate a failure. And there is nothing in the Channel Time Grant to indicate a failure. The only command that provides the type of indication required here is the stream command when its Action Type field is set to a value of 3. Consequently, it is my opinion that this paragraph is broken and should be deleted from the document. | Please delete the indicated paragraph. |  | X | O |  |  |  | Due in D08
259 | OI | 6 | 7.4.2 | 74 | 31-32 | T | CFP | The guaranteed start time parameter is redundant since the CFP duration and the superframe duration uniequely define the start of the CFP. One of these needs to be deleted. | Please clarify whether both parameters are required or only one of the two. | Guaranteed Start Time Removed | X | O |  |  |  | Due in D08
221 | WMS | 6 | 8.3.3 | 92 |  | T | CFP | Need to desciribe how SIFS fits in to GTS assignments: Is it at the end of a GTS, the start, or are the GTS slots assigned so that the end of one and the start of the next are spaced by a SIFS? | Bill will add text into 01259 to discuss Guard Time | Need a proposal. Possibly need to define the accuracy requiremejnts of the MAC clock. | D | A |  |  | Shvodian | In B. Shvodian Doc. 01439 | Pending results of further study. | x
236 | Vienna | 6 | 8.3.3 and others |  |  | T | CFP | Do we want to add static GTS slots for robustness and/or ease of implementation? See 01436r0 for justification |  |  | D | A |  |  | Shvodian | Table, proposal due 9/17/01
291 | WMS | 6 | 7.5.10 | 86 | 32 | E | Channel Status Response | Sentence need clarification. | "number of frames transmitted by the sender of this command" should be "number of frames transmitted by the sender of this command to the destination of this command. " | [6 empty] | Due in D08
292 | WMS | 6 | 7.5.10 | 86 | 32-36 | T | Channel Status Response | Not clear whether Tx and Rx frame count includes immediate ACKs. | Add clarification that Tx and Rx frame counts do not include the transmission of or reception of immediate Acks. | Discuss with R. Gubbi at Schaumburg
293 | WMS | 6 | 7.5.10 | 86 | 35-36 | T | Channel Status Response | Does the Rx Frame Count include errored frames? | Specify that the Rx Frame count does not include errored frames. | Word Correctly added. | [5 empty] | Due in D08
388 | ADH | 6 | 6.3.x.x | 37 |  | T | Channel Status Response | MLME-CHANNEL-STATUS.request/indication/response/confirm are not defined. | Please define the indicated MLME primitives. |  | X | O
283 | KAM | 6 | 7.5.5.1 | 82 | 13-14 | T | Channel Time Request | Kus is not enough resolution for the Duration between time slots. | Change the Duration between timeslots field to 16 bits, 8us resolution. | [6 empty] | Due in D08
285 | WMS | 6 | 7.5.5.1 | 83 | 16-19 | T | Channel Time Request | Why is minimum channel time in 32 us increments? Should be the same as requested channel time. | Change to 8 us increments, change table 23 as well.
284 | WMS | 6 | 7.5.5.1 | 83 | 5-6 and 10 | T | Channel Time Request | Stream ID is 16 bits. This field is only 8 bits. | The field should say "Stream Index" not Stream ID.
387 | ADH | 6 | 6.3.x.x | 37 |  | T | Channel Time Request | MLME-CHANNEL-TIME.request/indication/response/confirm are not defined. | Please define the indicated MLME primitives. |  | X | O
280 | ADH | 6 | 7.5.5.1 | 82 | 43 | T | Channel Time Request | … to channel time requested for a particular latency. | change sentence fragment to: … to channel time requested for a particular stream. … |  | X | O
122 | WMS | 6 | 7.5.5.2 | 68 | 39+ |  | Cmd Types | What is the purpose of the Channel Time Grant command if it has the same information as the Beacon? | Need to describe when and why the Channel Time Grant is used. | The frame is defined, but we need to add information about when is should be used. | D | A |  |  | Gubbi | ? | Defined in D05 Clause 7.5.1.2, Clause 8.2.3.2
255 | WMS | 6 | 7.3.3 | 72 | 24-26 | T | Command Frame | Not clear why one station would request more frames from another during the CAP. | Explain the purpose of this or remove it.
143 | ADH | 6 | 8.2.8 | 83 | 9-18 | T | CoordHndOvr | Does this mean that all the devices originally associated with the first AC now have to reassociate themselve with the new coordinator? Or does the new coordinator use the same PNID as the original coordinator? If it does reuse the PNID does this represent a security problem? |  | Auth. And Privacy Policies are being investigated. | X | A |  |  | Rasor
333 | ADH | 6 | 8.2.8 | 101 | 12 | T | CoordHndovr | Handover shall happen with a TBD parameter duration | Please define TBD |  | X | O
332 | ADH | 6 | 8.2.8 | 101 | 9 | T | CoordHndOvr | …PNC handover if allowed by the TBD security policy. Coordination Handover is dependent upon a defined Security policy. | Please define a viable security policy. |  | X | O
395 | WMS | 7 | 6.3.1 | 20 |  | T | CoordHndOvr | We probably need an MLME request and MLME indication primitive for PNC handover. |  |  | X | O
389 | ADH | 6 | 6.3.x.x | 37 |  | T | CoordHndOvr | MLEM-COORDINATOR-HANDOVER.request/indication/response/confirm are not defined | Please define the indicated MLME primitives. |  | X | O
331 | ADH | 6 | 8.2.8 | 101 | 8 | T | CoordSel | If the PNC-DesMode bit is set… | Please clarify the use of the PNC-DesMode bit. |  | X | O
394 | WMS | 7 | 6.3.9.2 | 34 | 44 | T | CoordSel | Need to clarify how SME knows that the station is PNC when a piconet is started or when PNC handover occurs.. | Add the following Sentence: ResultCode of SUCCESS indicates that the DEV is PNC. If another DEV is chosen as PNC or a piconet is already established, the result code shall be ALREADY_STARTED_OR_SYNCHed |  | X | O
396 | WMS | 7 | 65 | 40 | 24-44 | T | CoordSel | Should we add a MACPIBActingPNC PIB object? |  |  | X | O
273 | OI | 6 | 7.5.1 | 79 | 29-31 | T | CoordSel | … the free-air transmit power(in TBD) that is possible for the DEV. | Please provide TBD reference or definition |  | X | O
233 | Vienna | 6 | 8.2.8 | 88 |  | T | CoordSel | Need to add text describing how the PNC can review the capabilities of associating Devs and decide to perform PNC handover if the new device is more capable. Need to address Security Implications. |  | Already finished except for the xref to the security procedure which is TBD until authentication is defined. | D | A |  |  | Akahane | Table | Pending results of further study.
234 | Vienna | 6 | 8.2.8 | 88 |  | T | CoordSel | Need to add text describing how the PNC can review the capabilities of associating Devs and decide to perform PNC handover if the new device is more capable. Members may need to vote because the most capable PNC may not be the best geographically located. Sony's proposal 01304r0 addresses Piconet initialization, but an existing piconet also needs to be addressed. |  |  | D | A |  |  | Akahane | Table, proposal due 9/17/01 | Pending results of further study.
230 | Vienna | 4 | 8.1.3 |  |  | T | CoordSel | Need to clarify the use of the Des-mode bit in the coordinator selection process. |  |  | D | A |  |  | Shvodian | Proposal due from R. Gubbi, 09/17/01
207 | WMS | 4 | 6 |  |  |  | CoordSel | Update PIB and SAPs to reflect new coordinator comparison criteria | WMS to supply changes to PIB and SAPs to reflect the new coordinator comparison criterion. Review with Raju | WMS to provide additional detail in doc: 01/259r0 | A | W |  |  | Shvodian | Due 09/17/01 | Amendment approval
342 | ADH | 6 | 8.3.2.1 | 103 | 2 | E | CrossRef | … is reported through the MLME interface. | Please add the appropriate primitive name and its parameters along with an appropriate xref. |  | X | O
267 | ADH | 6 | 7.4.10 | 76 | 40 | E | CTA | Length = (n*12) is incorrect. | Change to Length = (n*6) |  | X | O
270 | ADH | 6 | 7.4.10 | 77 | 2 | E | CTA | …, then the source DEV shall send send broadcast frames only during that time slot. What time slot? | Remove the redundant send. Also clarify which time slot is being referenced. |  | X | O
271 | ADH | 6 | 7.4.10 | 77 | 9 | E | CTA | … by a CTA assigned with the PNC as the source and the destination. | Change sentence fragment to: …by a CTA assigned the source and destination address of the PNC. |  | X | O
218 | WMS | 6 | 7.4.10 |  |  | T | CTA | It may be worth while to add a bit to each CTA, and for the entire set of CTAs to indicate that a change in the CTAs has taken place. |  | Not really necessary if static GTS slots are allocated. | D | A |  |  | Shvodian | Table |  | x
248 | WMS | 6 | 7.2.1.4 | 68 | 35-38, 47-48 | T | Delayed-ACK Expedite Request | The Delayed-ACK expedite field is redundant with the Del-ACK Request field in the Frame Control Field 7.2.1.1.8 | Remove delayed ACK expedite from Figure 5, streamID field.
262 | WMS | 6 | 7.4.3 | 75 | 12-13 | T | DesMode | Definition of PNC-DES mode is not clear, | Should say: The PNC-Des-Mode is the designated mode of the DEV as currently set. The PNC-Des-Mode bit is set to one if the DEV is designated by a user to be PNC for the piconet. Otherwise the bit shall be zero. The PNC-Des-Mode bit shall always be set to zero if the DEV is not PNC capable.
229 | Vienna | 4 | 7.4.3 | 72 |  | T | DesMode | Need to clarify the use of the Des-mode bit. |  |  | D | A |  |  | Gubbi | Proposal due from R. Gubbi, 09/17/01
258 | OI | 6 | 7.4.1 | 73 | 49 | T | DEV-ID | Since device-ID is an 802 address, its transmission order needs to be such that the I//g bit is always transmitted |  |  | X | O
297 | ADH | 6 | 7.5.15 | 88 | 48-49 | T | DEV-Info | Length = 2 and Queried DEV-ID = 6 Which is correct? | Please indicate whether the DEV-ID is 6 or 2 octets in length. |  | X | O
298 | ADH | 6 | 7.5.15.2 | 89 | 19-22 | E | DEV-Info | Requested channel time for latency-1,,, What is latency? Is it a stream? This is inconsistent with earlier frame formats that reference stream-1, stream-2, etc…. | Provide text to clarify which is the correct word to use in these command fields. |  | X | O
382 | ADH | 6 | 6.3.7.2 | 31 | 23 | E | DisAssoc | ResultCode parameter name is inconsistent with frame type parameter defined in 7.5.4. | Change ResultCode to ReasonCode |  | X | O
383 | ADH | 6 | 6.3.7.3 | 31 | 46-47 | T | DisAssoc | Clause 6.3.7.3 MLME-DISASSOCIATION.indication describes the MLME primitive generated when a DISASSOCIATE.request is received from a DEV requesting to disassociate from the piconet, while Clause 8.2.6, p99, lines 42-46, describes the disassociation process. The issue here is that the disassociation.req frame type is specified as being sent as a directed frame. Consequently, there does not exist a mechanism which will enable devices not disassociating to update their association tables with the DEV-ID/AD-AD of the disassociated device. | Please modify the Disassociation.req description to support broadcast of the disassociate request frameType. This way associated devices could update their association table by removing the disassociated device-ID/AD-AD. |  | X | O
301 | ADH | 6 | 7.5.17 | 91 | 22 | E | DSAA | The DSAA field is illustrated… | Please provide a definition of the acronym DSAA |  | X | O
305 | ADH | 6 | 7.5.17 | 91 | 8-9 | E | DSAA | DSAA field What is DSAA? | Please provide a definition of the acronym DSAA |  | X | O
363 | ADH | 6 | 8.7.6 | 111 | 22-23 | T | Dup. Detect | … Duplicate detection is also required by the PNC when it is providing repeater service. The PNC shall detect multiple receptions of a frame and not send the repeated frame over the medium to the final receipient. Comment: This seems like an unnecessary complication. Why not make the repeater a dumb repeater. | Delete the indicated sentence from the clause. It adds an unnecessary level of complexity to the MAC. |  | X | O
256 | ADH | 6 | 7.3.4 | 72 | 38 | T | Encryption | The length of the encryption field is either 0 or <TBD>. | Please define the <TBD> |  | X | O
241 | WMS | 6 | 7.2 | 66 | 8-15 | T | FCS | FCS should not be sent if frame body is zero bytes. | Change 4 in the FCS octets to 0 or 4.
250 | WMS | 6 | 7.2.1.8 | 69 | 32 | T | FCS | FCS should not be sent if frame body is zero bytes. | Add the following sentence: If the frame bodiy has zero length (as in an immediate ACK frame) the FCS shal not be sent. In this case, the length of the FCS field is zero bytes.
242 | ADH | 6 | 7.2.1.1 | 66 | 30-31 | E | Frame Format | pad byte field should be pad bit | change pad byte field to pad bit. |  | X | O
245 | ADH | 6 | 7.2.1.1.4 | 67 | 28 | E | Frame Format | pad byte field should be pad bit |  |  | X | O
296 | ADH | 6 | 7.5.12 | 87 | 25-26 | E | Frame Format | Length = 2 is incorrect | Change to: Length= 4 |  | X | O
393 | WMS | 7 | 7 | 65 |  | E | Frame Format | Since there are now only 4 frame types, all DEVs shall be able to process all frames, except only PNC capable devices must be capable of creating beacon frames. | Modify "In addition" throught he end of the paragraph as follows: In addition, every DEV shall be able to construct these frame formats for transmission, and to decode frame formats upon validation following reception. The only exception is that a DEV that is not PNC capable need not be able to construct beacon frames. |  | X | O
368 | WMS | 6 | 11.4.4 | 135 | 18-21 | T | Frame Length | Why would you send FCS if there is no payload? That would require transmission of a minimum sized payload based on the interleaver. Immediate ACK should have no body, including no FCS. | Change te description of frame body length from "the shortest frame is just the FCS, 4 bytes, is encoded as 0x0000100" to "the shortes frame is zero bytes with no FCS" |  | X | O
369 | WMS | 6 | 11.4.4 | 135 | 18-21 | T | Frame Length | 11 bits gives 0-2047 bytes, not 0-2048 |  |  | X | O
370 | WMS | 6 | 11.4.4 | 135 | 18-21 | T | Frame Length | What is the meaning ov 0x0000100? Is this 100 hex? Binary? If binary, it should be 0b0000000000000100? |  |  | X | O
371 | WMS | 6 | 11.4.4 | 135 | 18-21 | T | Frame Length | Frame body length is the wrong term. This should be MPDU length, because it includes MAC header, Frame body and FCS | Change the name from "Frame Body Length" to "MPDU length" |  | X | O
340 | ADH | 6 | 8.3.2.1 | 102 | 36 | E | Grammar | …is performed in order to send frames during the CAP. | Please change the indicated sentence fragment to: … is performed when sending frames during the CAP. |  | X | O
341 | ADH | 6 | 8.3.2.1 | 102 | 52 | E | Grammar | … is not correctly received by the DEV, … | Please change the indicated sentence fragment to: … is not corrrectly received by the transmitting DEV, … |  | X | O
337 | ADH | 6 | 8.3.1 | 102 | 9-10 | E | Grammar | … In order to declare the detection of a RIFs the channel shall be idle for full contiguous aCCADetectionDuration after a SIFS after the end of the transmission by the DEV. … Huh? | Please clarify the meaning of this sentence. I got lost after the second "after". Or change the sentence as indicated here: In order, to declare the detection of a RIFS, the channel shall be idle for a full contiguous aCCADetectionDuration after a SIFS. |  | X | O
345 | ADH | 6 | 8.3.3 | 103 | 13 | E | Grammar | … The process of channel time request and allocation are described … | Change sentence fragment to: … The process of channel time request and allocation is described... |  | X | O
346 | ADH | 6 | 8.3.3.2 | 103 | 33-34 | E | Grammar | The PNC may announce the slot assignments in directed or … | Change the sentence to: In addition, the PNC may announce the slot assignments in either a directed or a broadcast channel time grant command. |  | X | O
347 | ADH | 6 | 8.3.2.2 | 103 | 41-42 | E | Grammar | … for transmission of the return Del-ACK unlike in the case of Imm-ACK… | Change sentence fragment to: "… for transmission of the return Del-ACK. Where, unlike the Imm-ACK case, the sender of the data frame guarantees the time required for the Imm-ACK. |  | X | O
343 | ADH | 6 | 8.3.3 | 103 | 9-10 | E | Grammar | The channel access during the CFP …. | Change the sentence indicated to: Channel access, during the CFP, is based on TDMA in which all slots have a guaranteed start time. |  | X | O
348 | ADH | 6 | 8.3.3.2 | 104 | 1 | E | Grammar | … type of interference they are subjected to. … | Change sentence fragment to: … type of interference to which they are subjected. … |  | X | O
355 | ADH | 6 | 8.5 | 105 | 37 | E | Grammar | … for which they are designed to support… | Change to … for which it is designed to support… |  | X | O
356 | ADH | 6 | 8.5 | 105 | 38 | E | Grammar | … as many as it desires to source and sink … | Change the indicated sentence to: … as many as it is designed to source and sink including those additional streams needed to support repeater service. |  | X | O
364 | ADH | 6 | 8.8 | 111 | 34 | E | Grammar | … shall respond with aprobe response command, 7.5.7, with its response within aProbeResponseDelay. | Change the sentence to: … 7.5.7, within aProbeResponseDelay. |  | X | O
247 | ADH | 6 | 7.2.1.4 | 68 | 33 | E | Grammar | … in for data frames. … | remove in from the indicated sentence fragment. |  | X | O
257 | ADH | 6 | 7.4 | 72 | 43 | E | Grammar | … described in the following manner;. … | Change … following manner to" in their respective subclauses.. |  | X | O
261 | ADH | 6 | 7.4.3 | 74 | 43 | E | Grammar | … field shall not while the DEV… | change this fragment to …field shall not change while the DEV… |  | X | O
263 | ADH | 6 | 7.4.5 | 75 | 51 | E | Grammar | … to which the PNC is intending to move the piconet over to. | Change this sentence fragment to: … to which the PNC is intending to move the piconet. |  | X | O
269 | ADH | 6 | 7.4.11 | 77 | 15 | E | Grammar | …where the DEV is either the source or destination, including group or multicast destinations. … | Change the sentence fragment to: …where the DEV is either the source or destination. The destination address also includes group or multicast addresses. |  | X | O
274 | ADH | 6 | 7.5.1 | 79 | 33 | E | Grammar | … that is achievable by PHY of the DEV. | Change the sentence fragment to: … that is achievable by the DEV PHY. |  | X | O
275 | ADH | 6 | 7.5.1 | 79 | 39-40 | E | Grammar | … DEV my extend this time in its frame which shall be adapted by all the … | change the sentence fragment to: …DEV may extend this time via its frame which shall be adopted by all the … |  | X | O
279 | ADH | 6 | 7.5.3 | 81 | 43 | E | Grammar | … as its address in the piconet in all its future communications… | Change the sentence fragment to: as its address in the piconet during all its future communications… |  | X | O
281 | ADH | 6 | 7.5.3 | 82 | 6 | E | Grammar | … The ATP is the finalized value of the for the timeout period. … | Change the sentence fragment to: … The ATP is the finalized value for the association timeout period. … |  | X | O
282 | ADH | 6 | 7.5.5.1 | 83 | 17 | E | Grammar | … time slot is smaller the time indicated… | Change sentence fragment to … time slot is smaller than the time indicated... |  | X | O
290 | ADH | 6 | 7.5.10 | 86 | 20 | E | Grammar | DEV know the current channel condition at sending DEV… | Change sentence frag to: DEV know the current channel condition at the responding DEV. |  | X | O
294 | ADH | 6 | 7.5.11 | 87 | 12 | E | Grammar | that the PNC is being requested to buffer the … | Change the sentence frag to: that the PNC is requesting to buffer the … |  | X | O
314 | ADH | 6 | 8.1 | 95 | 31-32 | E | Grammar | If the link between two DEVs is not satisfactory, then either of those DEVs…. | Make these changes to the indicated sentence: If the link between two DEVs is not satisfactory, then either of the DEVs may request the PNC to provide repeater service fo the entire link. |  | X | O
318 | ADH | 6 | 8.2.1 | 96 | 17 | E | Grammar | During searching …. | Change sentence to: While searching, |  | X | O
319 | ADH | 6 | 8.2.1 | 96 | 18 | E | Grammar | If the DEV is allowed… | Change sentence to: If the searching DEV is allowed… |  | X | O
320 | ADH | 6 | 8.2.1 | 96 | 7-8 | E | Grammar | During such scanning the DEV shall ignore all the received frames… | Make these changes to the indicated sentence: While scanning the DEV shall discard all received frames having a different PNID than the one for which the DEV is searching. |  | X | O
321 | ADH | 6 | 8.2.1 | 96 | 8-9 | E | Grammar | Hence all the following… This sentence adds no value. | Delete the indicated sentence from the clause. |  | X | O
322 | ADH | 6 | 8.2.5 | 97 | 49 | E | Grammar | …exchanged only in the CAP of the superframe. | change sentence fragment to: …exchanged in the CAP of the superframe. |  | X | O
324 | ADH | 6 | 8.2.5 | 98 | 1 | E | Grammar | …be acknowledged by the PNC by sending an ACK frame. | Delete the indicated "by" |  | X | O
325 | ADH | 6 | 8.2.5 | 98 | 11 | E | Grammar | Therefore, no ACK required… | Change sentence to: Therefore, no ACK is required… |  | X | O
326 | ADH | 6 | 8.2.5 | 98 | 12 | E | Grammar | ...shall compare its own device-ID … | Delete the indicated word "own" its redundant to its |  | X | O
327 | ADH | 6 | 8.2.5 | 98 | 2 | E | Grammar | … that the DEV has been associated. | Replace "has been" with "is". |  | X | O
329 | ADH | 6 | 8.2.5 | 98 | 9-11 | E | Grammar | If an ACK was required…. | Delete the indicated sentence from the clause. |  | X | O
330 | ADH | 6 | 8.2.5 | 99 | 36-37 | E | Grammar | …shall be assigned to the coordinator fuction… | replace fuction with function. |  | X | O
334 | ADH | 6 | 8.3 | 101 | 34-41 | T | Guard Time | Figure 49 Superframe structure does not include guardtime | Please add Guardtimes between GTSs in diagram. |  | X | O
235 | Vienna | 6 | 7.5.2 and 8.TBD |  |  | T | Heartbeat | Should we add an unsolicited heartbeat function? An unsolicited Heartbeat function may be beneficial for power save devices as described in Sony document 01306r0. |  |  | D | A |  |  | Akahane | Table, proposal due 9/17/01 | Pending results of further study.
335 | ADH | 6 | 8.3.1 | 101 | 47 | T | IFS | There is need, in this clause, for an IFS timing relationship diagram with parameters. This diagram shall be similar to the one illustrated on page 85 of ISO/IEC 8802-11:1999(E) | Please include the requested diagram. |  | X | O
336 | ADH | 6 | 8.3.1 | 102 | 6-7 | T | IFS | … Beacon frame transmission shall use RIFS for their transmission. Huh? Why? | Please strike this sentence, it is technically incorrect. |  | X | O
240 | ADH | 6 | 7.2 | 66 | 18 | E | Label | Figure 3 - MAC frame format label is in the wrong position | Move the label from line 18 to line 15. |  | X | O
11 | WMS | 6 | 6.3, 6.7, 6.8 | 15 | 32-42 |  | MLME SAP | It would be nice to have a list of primatives and a short description | Please add the appropriate definitions. | R. Roberts will add an MLME primitives table similar to the one for the PHY-SAP. Also add MAC-SAP and PLME-SAP tables | A | A |  |  | Roberts | Due 10/9/01 | R - Rejected | Z - Withdrawn
249 | WMS | 6 | 7.2.1.5 | 69 | 7 | E | MSDU/MCDU. | MSDU/MCDU should be replaced by MPDU. | Replace MSDU/MCDU with MPDU
339 | WMS | 6 | 8.5 | 105 | 33 | T | Multicast | There is currently no mechanism specifiedx to set up a multicast stream
223 | Vienna | 6 | 5 |  |  | E | Overview | Clause 5 needs updating to match clause 7 and 8 |  |  | D | A |  |  | Gilb | Assigned
4 | ADH | 2 | 5.2 | 11 | 30-31 | E | OvrView | This sentence is inaccurate. | This sentence needs to be struck. |  | D | A |  |  | Gilb | Due 10/9/01 | D - Dispatched | W - Written
3 | ADH | 2 | 5 | 12 | 30 | E | OvrView | The overview clause is incomplete. | Please complete. |  | D | A |  |  | Gilb | Due 10/9/01 | X - received | O -Open
5 | ADH | 2 | 5.2.2 | 12 | 4-5 | E | OvrView | This sentence needs to be reworked to emphasize the concept of access portals and minimize the inferred LAN capability. | Please rework sentence to minimize inferred LAN bias. |  | D | A |  |  | Gilb | Due 10/9/01 | A - Accepted | C - Closed
317 | WMS | 6 | 8.2 | 96 |  | T | Passive Scan | Need to define passive scanning for any PNID. 8.2 currently only addresses searcing for a specific PNID.
365 | ADH | 6 | 8.8 | 111 | 41 | T | Peer Discovery | … any DEV may send any directed command frame to any other DEV in the piconet to determine if the destination DEV is still present in the piconet. Comment: This sentence implies that the DEV can send a Retransmission req, Channel Status request, Association req, Disassociation req, and Sleep state req as "pings" to the destination device. Doesn't this get confusing if all the transmitting DEV wants to do is determine whether the destination DEV is present? | Either delete the indicated sentence or specify a new directed command which will fulfill this requirement. |  | X | O
246 | ADH | 6 | 7.2.1.2 | 68 | 13 | T | PNID | … The PNID remains constant during the life of the piconet. The question regarding this sentence is: "Does this imply that the PNID is a transient value? Does this mean that when the PNC or the piconet AC go away, the PNID is not persistent? | Change the text indicated to: "… The PNID remains constant during the current instantiation of the piconet and may be persistent for multiple sequential instantiations of the same PNC initiated piconet. |  | X | O
366 | ADH | 6 | 8.12 | 115 | 1-33 | T | Power Mgt | Provide the Bain/Shrader text for this clause | Provide the Bain/Shrader text for this clause |  | X | O
170 | ADH | 6 | 8.5.3 | 94 | 48-49 | T | Priorities | I disagree with the statement that the priority algorithms are beyond the scope of this standard. One of the problems BT type devices are running into is the problem of interoperability. If two or more devices have different rules for priority of data transmissions, I would expect a failure to communicate. | 802.1D describes the use of priorities, we will add one bit for for Isochronous/asynchronous. See 293r1 |  |  | A |  |  | Heberling |  | Amendment Approval
360 | ADH | 6 | 8.5.3 | 108 | 11-12 | T | Priority mgt | … DEVs shall transmit a higher priority stream before lower priority streams, except for isochronous streams. … Comment: So isochronous streams are of higher priority than other stream types. But I thought there were only two stream types: stream and non stream. From the description provided here streams have higher priority than non-streams. How does one determine the difference in priority of streams? | Please clarify the content of this clause. |  | X | O
286 | ADH | 6 | 7.5.7 | 84 | 39-49 | T | Probe Rsp | The two paragraphs contained here are a complete cut & paste of the paragraphs written for 7.5.6 | Provide text that defines the content of the response. |  | X | O
265 | ADH | 6 | 7.4.8 | 76 | 21-24 | T | PS | Clause is TBD | Please define the <TBD> |  | X | O
102 | ADH | 6 | 7.4.8 | 64 | 5 | T | PwrMgt | Power Save Parms are TBD. | Please define TBD PwrSve Parms | Make changes indicated in 01/262r3 | D | A |  |  | Bain | Table
390 | ADH | 6 | 6.3.x.x | 37 |  | T | PwrMgt | MLME-POWER-MANAGEMENT.request/indication/response/confirm are not defined. | Please define the indicated MLME primitives. |  | X | O
13 | RDR | 6 | 6.3.1 |  |  | T | PwrMgt | MLME-Powermanagment.request needs to be made consistent with 15.3 Powermanagement Policy |  | Apply changes in document 01/262r3 | D | A |  |  | Gilb | Due 10/9/01 | Q-Questioned | U-Unsatisfied
177 | WMS | 01/262r2 |  |  |  |  | PwrMgt | Should we support remote wake-up? |  |  | D | A |  |  | Bain | Tabled, proposal due by 9/17/01
306 | ADH | 6 | 7.5.17 | 92 | 15-16 | T | QoS | In the QoS parameter field there are two Stream ID fields one in the first level QoS field and a second buried in the CTRB field. There seems to be an implied race condition between these two fields | Please provide clarification. |  | X | O
391 | ADH | 6 | 6.3.x.x | 37 |  | T | Repeater | MLME-REPEATER.request/indication/response/confirm are not defined. | Please define the indicated MLME primitives. |  | X | O
224 | Vienna | 4 | 8.8 | 99 |  | T | Repeater | What are the permitted ACK policies for for the repeater function? How do they function? | Needs clarification to handle point to point and/or end to end ACK policies. Raju thinks delayed ACK is needed. |  | D | A |  |  | Gubbi | Proposal due from R. Gubbi, 09/17/01 | Approval of text in col. K
300 | WMS | 6 | 7.5.16.1 | 89 | 41+ | E | Retransmission Request | Why is this called Retransmission request instead of Delayed Ack? If you get all the frames correctly you never need to request a retransmisison, but you DO need to send acknowledgements. | Change name to Delayed Acknowledgement
372 | ADH | 6 | 6.3.2.1 | 21 | 39-40 | T | Scan | PNID Type is 2 octets, Valid Range is 0-65535, Description: Identifies either a generic or specific PNID. | Please replace the PNID attribute column entries with the text provided. |  | X | O
373 | ADH | 6 | 6.3.2.2 | 22 | 35-54 | T | Scan | PiconetDescription parms are incorrect. | Please replace the table with these elements: PNID, DEV-ID, PiconetSynchParms, TPC-Parms, ChannelChangeParm, CTA-Parms |  | X | O
251 | ADH | 6 | 7.2.1.1.9 | 68 | 4 | T | SEC | …, the frame body field contains the encrption fields as defined in <TBD>. | Replace TBD with reference to text describing the encryption mechnism. |  | X | O
264 | ADH | 6 | 7.4.7 | 76 | 17-19 | T | SEC | Clause is TBD | Please define the <TBD> |  | X | O
302 | ADH | 6 | 7.5.17 | 91 | 43 | E | SEC | The security field definition is TBD | Please provide definition |  | X | O
361 | ADH | 6 | 8.7.2 | 109 | 22 | E | Spelling | …SIFS durtion after the end… | Replace durtion with duration.. |  | X | O
276 | ADH | 6 | 7.5.1.3 | 80 | 11 | E | Spelling | Batter/AC power | Change to Battery/AC power |  | X | O
299 | ADH | 6 | 7.5.15.2 | 89 | 29 | E | Spelling | indicted | replace indicted with indicated. |  | X | O
384 | ADH | 6 | 6.3.9.1 | 33 | 45-50 | T | Start | MLME-START.request parameters are inconsistent with parameters suggested in clauses 8.2.1, 8.2.3, 7.5.1 | Please rename BeaconPeriod to ChannelScanDuration. Please delete PhyParameterSet. Also add these parameters to the list: PNID, ChannelList,ChannelScanDuration,Capability IE, PowerSource, MaxGTS, TxPwrLevel, DEV-ID, CSTimeout. |  | X | O
385 | ADH | 6 | 6.3.9.1 | 34 | 3-12 | T | Start | Incorrect or missing parameters in MLME-START.req table. | Please remove the incorrect parameters and add the missing ones with definitions to the table. |  | X | O
386 | ADH | 6 | 6.3.9.2 | 34 | 41-42 | T | Start | MLME-START.confirm parm table is missing an error message. | Please add this error message to the indicated table: No_Channels_Available |  | X | O
287 | ADH | 6 | 7.5.8.1 | 85 | 12-13 | T | Stream Mgt | Channel Time for latency-1,,, What is the latency? Is it a stream? This is inconsistent with earlier frame formats that reference stream-1, stream-2, etc… | Provide text to clarify which is the correct word to use in these command fields. |  | X | O
288 | ADH | 6 | 7.5.8.1 | 85 | 20 | T | Stream Mgt | The format of channel time for a given latency is illustrated… | Provide text to clarify which is the correct word to use (latency or stream). |  | X | O
303 | ADH | 6 | 7.5.17 | 91 | 43-45 | E | Stream Mgt | The security field definition comes before the ACK policy field. | Please place the ACK policy field definition before the security field definition |  | X | O
307 | ADH | 6 | 7.5.17 | 92 | 36 | T | Stream Mgt | The priority field in stream ID field contained in channel time requet block… | Please indicate where the priority field is located in the stream ID field. |  | X | O
90 | ADH | 6 | 7.3.4 | 59 | 43 | t | Stream Mgt | Too many TBDs for the Stream Data frame format. | Please provide specific ranges or values regarding Encryption field and max length of the data field. | Raju to provide feedback in 292r1 | D | A |  |  | Gubbi | ? | Dependent upon Security/Privacy recommendations
308 | WMS | 6 | 7..5.17 | 91 | 49 | T | Stream Mgt | What valued does the PNC set the direction bit to when sending stream management frames to a destination? | Clarify that the PNC sets the direction bit to zero on stream management frames to the destination.
310 | WMS | 6 | 7.5.17 | 92 | 13-30 | T | Stream Mgt | ACK policy should be included in the QoS parameters. Also need to limit the number of frames for receive window. | Add a max receive window frames, where zero specfies no ACK, 1 specifies immediate ACK, greater than one allows delayed ACK.
168 | Ol | 6 | 6.3.10, 6.3.11 | 92 | 27-28 | T | Stream Mgt | These stream management signals need to be defined in the MAC management clause: MLME-Stream-Connect.request, MLME-Stream-connect.indication, MLME-Stream-Disconnect.request, MLME-Stream-Disconnect.indication | Need to define the parameters, "when generated", and "effect of receipt" for each of the stream management entities identified to the left. Add to section 6. |  | D | A |  |  | Roberts | Pending resolution from Heberling |  | x
309 | WMS | 6 | 7.5.17 | 92 | 3 | T | Stream Mgt | How is "bandwidth allocation failure" different from "system resources unavailable" | Define "bandwidth allocation failure."
313 | WMS | 6 | 7.5.17 | 92 | 30 | T | Stream Mgt | 8 bit pkt window size only allows 256K Octets, which limits rate to 20 Mbps with a 100 ms superframe.
311 | WMS | 6 | 7.5.17 | 92 | 45 | T | Stream Mgt | What is the purpose of the "minimum rate parameter"? | Should be changed to "minimum channel time." Minimum rate is not useful.
312 | WMS | 6 | 7.5.17 | 92 | 45-54 | T | Stream Mgt | What are all these values (minimum rate, peak rate, average rate, max burst size, average frame size) set to for data or other applications where these values are unknown?
357 | ADH | 6 | 8.5.1 | 106 | 12-48 | T | Stream Mgt | The stream connection Message sequence chart does not include references to the QoS parms identified in clause7.5.17. In particular, the bandwidth requirements. Comment: The bandwidth request parms are essential elements of the stream connection process. | Please update the Stream connection MSC with references to the QoS parms and who has responsibility for their modification. |  | X | O
358 | ADH | 6 | 8.5.1 | 107 | 31-32 | T | Stream Mgt | … may use a data frame with the stream-ID set for non-stream data as described in 7.3.4. Comment: There seems to be a logical inconsistency here. If a non-steam data link is needed how does the DEV determine whether its bandwidth request is rejected? There is no mechanism for communicating this situation. | I will provide a proposal during the Bellevue meeting to address this situation. |  | X | O
359 | ADH | 6 | 8.5.2 | 107 | 47-48 | T | Stream Mgt | … If the DEV initiating such a transaction is not the PNC, it shall also send this command to the PNC.(Comment: this implies to me that the DEV sends the stream disconnect command twice. Once to the destination DEV and the second to the PNC.) The PNC shall then communicate the disconnection to the other involved DEV via the stream management command. Comment: Huh? There seems to be a logical inconsistency here. Does the DEV send the disconnect to the DEV and to the PNC or does it just send one disconnect request to the PNC? | Please clarify the logical inconsistency identified in lines 47-48. |  | X | O
52 | WMS | 6 | 6.3.10, et. al |  |  |  | Stream Mgt | How is a packet from the upper layers mapped to a Stream index? | Look at how 802.11e is doing it. May need convergence layer. Maybe use "routing information from MA Unidata.request |  | D | A |  |  | Heberling | Tabled | Pending results of further study.
268 | ADH | 6 | 7.4.6 | 76 | 6-7 | T | Supported Rates | … as described in the TBD 11.x.y.z… | Please define the <TBD> |  | X | O
351 | ADH | 6 | 8.4 | 104 | 37-40 | T | Synch | … at the end of the beacon header… relative to the end of the beacon header. … where it expects the end of the beacon. | Please change the indicated fragments to: … at the beginning of the beacon preamble… relative to the beginning of the beacon preamble. … where it expects the beginning of the beacon preamble. |  | X | O
352 | ADH | 6 | 8.4 | 104 | 38 | T | Synch | Figure 50 shows t=0 at the end of the header. Shouldn't it be at the beginning of the preamble? | Please change the diagram to illustrate the correct reference Time-zero. |  | X | O
354 | ADH | 6 | 8.4.4 | 105 | 28 | T | Synch | … for more than aConnectionTimeOut period… Comment: Is this the same as the AssociationTimeOutPeriod (ATP)? | Please clarify this parameter. Is it a PIB value? Is it the same as ATP? Is it consistent with the PowerSave Time out parms? |  | X | O
252 | WMS | 6 | 7.3.1 | 70 | 36-54 | T | Table | Table 58 does not mention Stream ID and Sequence Number. | Add Stream ID and Sequenc Number and state that they are ignored on reception
253 | WMS | 6 | 7.3.2 | 71 | 11-29 | T | Table | Table 59 does not mention Stream ID and Sequence Number. | Add Stream ID and Sequenc Number and state that they are ignored on reception
254 | WMS | 6 | 7.3.2 | 71 | 35 | E | Table | Why is stream ID mentioned separately instead of in the table? | Put Stream ID into the table.
353 | ADH | 6 | 8.4.1 | 104 | 44 | T | Time Accur | … the accuracy of the timer to be +/-0.01% of its resolution. Comment: This doesn't seem sufficiently accurate. Particularly, since we are going to be specifying guardTime intervals. Guardtimes are going to be dependent upon the clock drift. Consequently, I see a need for a more precise specification here. | Please provide the specification in PPM. |  | X | O
367 | ADH | 6 | 8.13 | 115 | 35-38 | T | TPC | Provide the Gubbi/Roberts text for this clause. | Provide the Gubbi/Roberts text for this clause. |  | X | O
392 | ADH | 6 | 6.3.x.x | 37 |  | T | TPC | MLME-TxPOWER-CONTROL.request/indication/response/confirm are not defined. | Please define the indicated MLME primitives. |  | X | O
266 | ADH | 6 | 7.4.9 | 76 | 25-27 | T | TPC | Clause is TBD | Please define the <TBD> |  | X | O
295 | OI | 6 | 7.5.11 | 87 | 15 | T | TU | TU is used many places but has not yet been defined. | Please define TU |  | X | O
243 | ADH | 6 | 7.2.1.1.1 | 66 | 42 | T | Version | …A DEV that receives a frame with ahigher revision level than it supports will discard the frame without indication to the sending DEV. | The receiving DEV should inform the transmitting device with the higher revision level that the receiving DEV can not support the higher level revision. |  | X | O
36 | MkS | 6 | 7.2 |  |  |  |  | The implementation of almost any second mode of MAC operation will require some additional information in the MAC header. I therefore request 1 byte be reserved so that the possibility of additional MAC functionality is not eliminated from the standard. |  | This item to be discussed during telecons. Mark Schrader will do a submission for Portland to add a MAC mode information element. | X | A |  |  | Schrader | Tabled, proposal due by 9/17/01 | Pending Presentation
272
398 | [7 empty] | Need to add

## Closed issues
| Color Codes |  |  |  | Changes approved |  |  | Green Color done manually
|  | Proposal pending |  |  | Assigned
|  | Proposal pending |  |  | Open, not assigned
Issue Number | Commenter's Initials | Draft Version Number | Clause number e.g., 8.10.2 | Page number e.g., 1-1130, etc. | Line number e.g., 1-54 | Type of comments (E/e/T/t) | Class of Problem | Comment/Rationale (Issue and reasoning behind it.) | Recommended change (What change(s) it would take to make this clause acceptable.) | Disposition/Rebuttal (Do not write here during ballot phase; this is for comment resolution phase.) | Issue Status X,D,Q,A,R | Resolution Status O,W,C,U,Z | Date Entered | Date Completed | Asignee | Amendment Doc # |  | Issue Status | Resolution Status
2 | WMS |  | 4. | 8 |  |  | Acronyms | IFS, RIFS, SIFS, TIFS, MIFS are missing from the acronym clause. | Please provide accronyms | Please add acronyms to acronym list and definition to definitions list. | A | C |  |  | Gilb | Done in D06 |  | X - received | O -Open
6 | ADH | 2 | 6.1 | 13 | 16-17 | t | SNMP | What is meant by standard management protocols? Does this statement imply support for SNMP? | Please Clarify | R. Roberts will remove reference to SNMP | A | C |  |  | Roberts | Done in D06 |  | D - Dispatched | W - Written
12 | ADH | 2 | 6.3.1.1 | 16 | 19-24 | t | Synch | Are we going to support a DTIM mechanism? | Please provide justification. |  | D | C |  |  | Bain | Withdrawn |  | A - Accepted | C - Closed
22 | MCO | 6 | 6.3.3.1 | 19 | 46 | T | Synch | Should Operation Rate Set be added back in? | Resolve this. | Will be in draft 5. Voted on in 222r1 in Portland, now in capability information field. Need to add data rate to bit mapping in PHY section. | A | C |  |  | Gilb | Due 9/17/01 |  | R - Rejected | Z - Withdrawn
39 | WMS | 2 | 7.1.3.1.3 | 49 | 1 | E | Stream-Data | Need to define Stream-Data | Change "Stream-Data" to "Data (Stream or non-Stream)" everywhere in the draft. | Do Global change. Maybe find a better name. | A | C |  |  | Gubbi | Done in D05 |  | Q-Questioned | U-Unsatisfied
48 | ADH | 2 | 7.1.3.2 | 50 | 36 | T | PNID | How is the PNID generated? Is it based on the coordinator's MAC address? Is it some PRN generated 2 octet value? | Please Clarify. | Add following to 8.1.2 :"Seed for the randomization process is required to choose the PNID shall be 48bit device ID of the PNC." | D | C |  |  | Gubbi | Pending | Amendment approval if col. K text
51 | ADH | 2 | 7.1.3.4 | 51 | 7 | t | StrmMgt | What are considered non-stream data? Command packets? ACKs? What about short message packets? Is an asynchronous bulk transfer of data considered a non stream data type? Or is it a type of streaming data? | Add the following text to the last paragraph in section 7.2.1.4 in 292r1: The use of a stream connection for asynchronous data is up to the device. | Add the following text to the last paragraph in section 7.2.1.4 in 292r1: The use of a stream connection for asynchronous or isochronous data is up to the device. | D | C |  |  | Gubbi | Done in D05
68 | WMS | 2 | 7.2.3.x | 55 | 19 | t | CoordSel |  | Recommend changing the Coordinator Selection Fields to more appropriate criteria. | WMS to provide exact details in doc: 01/259r0. Reviewed at Vienna ad hoc | A | C |  |  | Shvodian | Done in D06
71 | WMS | 2 | 7.2.4 | 56 | 16-19 |  | Assoc | Why is Network ID field null in Association Requests from un-associated STAs? | Recommend using in the MAC header the PNID of the PicoNet the device is trying to join. | Replace current text in L16-19 with proposed text | A | C |  |  | Gubbi | Done in D07
73 | WMS | 2 | 7.2.4 | 56 | 25-35 |  | Assoc. | What is the purpose of the Allocated Station Address field in the Association Request command? If it is always FE, does it serve any purpose? | If the purpose is to keep the request and response the same, it makes sense. | Need Feedback from Raju as to why. | D | C |  |  | Gubbi | Withdraw
80 | ADH | 2 | 7.2.5 | 57 | 44 | E | Assoc | Reason codes should be defined here first |  |  |  | C |  |  | Gubbi | Done in D05
86 | WMS | 2 | 7.2.6 | 58 | 8-14 |  | Assoc. | Why is station device ID needed in Disassociation Request? Is this a directed Frame or broadcast? |  | Need Feedback from Raju as to why. |  | C |  |  | Gubbi | Withdrawn
95 | WMS | 2 | 7.3.2 | 61 | 39-40 |  | Superframe Duration | 0-524280 uS is too large a range for superframe duration | Change minimum beacon interval to .5 Kus and maximum to 100 Kus | Adopt this proposal. Add to MAC committee resolution. | A | C |  |  | Gubbi | Done in D05
103 | ADH | 2 | 7.3.8 | 64 | 9 | T | TxPwr | Transmit Pwr Cntl Parms are TBD. | Please define. |  |  | C |  |  |  | Done in D07
111 | WMS | 2 | 7.3.9 | 64 | 14+ |  | CTA | Is there any way to limit the number of CTAs that are assigned to a terminal? Would this be a negotiated parameter? | Please Clarify | WMS to provide exact details in doc: 01/259r0. Reviewed at Vienna ad hoc | A | C |  |  | Gubbi | Pending | Approval of Amendments
120 | WMS | 2 | 7.4.1.1 | 68 | 11-22 | T | Latency | What does "Latency" Mean in a channel time request? Is it latency from the time the request is made until the slot is assigned? The time bewtween slots? | Define "latency" | The name was changed from latency to duration between slots | D | C |  |  | Gubbi | Done in D05 | 7.5.1.1
121 | WMS | 2 | 7.4.1.1 | 68 | 1-9 | T | Latency | Why does a station make requests for different levels of "latency?" Doesn't isochronous demand low latency and asynchronous is latency insensitve? | Remove Latency from the channel time request since it is implied by isochronous vs. asynchronous. | Get feedback from Raju. Latency removed from channel time requests in 01292r1, but Channel time request is different than wat was discussed in Orlando. | D | C |  |  | Gubbi | Done in D05 | 7.5..1.1
127 | WMS | 2 | 7.4.4 | 71 | 9-35 |  | Cmd Types | Is the Remain Quiet Command needed, or can the coordiator accomplish this by setting CTAs to zero? | Remove Remain Quiet Command | Remove Remain Quiet Command | A | C |  |  |  | Withdraw
128 | ADH | 2 | 7.4.6 | 72 | 46 | t | CoordHndOff | What is the preferred range for this duration? | Please Clarify. | Variables to be added: minHandOvrTO(.25sec) and maxHandOvrTO(1.0sec).Also change HandOvr timer resolution to 1Kus . | D | C |  |  | Gubbi | Done in D06 | Amendment Approval
129 | ADH | 2 | 7.4.7.1 | 73 | 20-21 | E | DevInfo | Line 21 is unclear in its meaning | Please clarify. | In Figure 33, Clause 7.5.10.1/d05 remove Requester Dev. ID field | D | C |  |  | Gubbi | Done in D06 | AmendmentApproval
133 | ADH | 2 | 8.1.3 | 81 | 36 | t | CoordSel | Why doesn't the losing AC just keep itsTx quiet? Why does it need to send a signal indicating that it has removed itself? |  | Delete directed frames since they are not possible and have losing ACs remain quiet. | D | C |  |  | Heberling | Done in D07 | Pending results of further study.
134 | ADH | 2 | 8.1.3 | 81 | 39 | t | CoordSel | If all the ACs were comparing parameters then the one with the highest ranking would already know that it is the new coordinator for the piconet. | Simplify Coordinator Selection Process. | Delete directed frames since they are not possible and have losing ACs remain quiet. | D | C |  |  | Heberling | Done in D07 | Pending results of further study.
141 | ADH | 2 | 8.1.6 | 82 | 45 | E | Auth | The Authentication Clause should come before the Association Clause. Why allow Association if you haven't been Authenticated to some level of Security? | Move Auth. Clause 8.1.6 to 8.1.4 and slip 8.1.4 to 8.15 and 8.1.5 to 8.1.6. I42 | Auth. And Privacy Policy is being investigated. | X | C
142 | ADH | 2 | 8.1.7 | 82 | 49-54 | T | DevReg | This scenario works fine for a non secure public implemetation. However, there needs to be a more secure scenario provided as well. | The policies of device registration and association are dependent upon the Security policies defined for a piconet environment. | Auth. And Privacy Policies are being investigated. | X | C
146 | ADH | 2 | 8.2.1 | 84 | 23 | t | IFS | How long is a slot? Is this slot the same as a GTS? Or is it the same as a backoff slot? | Please clarify. | MAC committee amendment recommends aBackoffSlot see doc 01/355. | D | C |  |  | Gilb | Done in D07 | J. Gilb editing D05
166 | WMS | 2 | 8.3.1 | 91 | 18+ | T | TSF | If we get rid of TSF and replace it with beacon number and offset time, a reference point will be required. The current reference point is the TSF field. | Replace the TSF and substitute a beacon count and offset time. | WMS to provide a detailed superframe timing diagram in 01259. Also WMS to synch with S. Ling and J.Gilb in the phy committee. | D | C |  |  | Shvodian | Done in D06
167 | Ol | 2 | 8.3.2 | 91 | 42-43 | t | TSF | Clock accuracy (or MAC clock accuraccy): +/- % accuracy or x ppm? | Please specify |  | D | C |  |  | Shvodian | Done in D05 | 8.3.2
176 | ADH | 2 | 8.10 | 98 | 38 | T | PwrMgt | Power Mgt. needs to be defined. | Please Define. | Make changes indicated in 0/1262r3 | D | C |  |  | Bain | Done in D07
178 | ADH | 2 | 8.11 | 98 | 42 | T | TxPwr | Transmit Power Cntrl needs to be defined. | Please define. |  | D | C |  |  | Roberts, Bain, Gubbi | Table
181 | ADH | 2 | 11.4.1 | 115 | 17 | T |  | What is the PHY header format? | Please define |  | D | C |  |  | Gilb | Done in D05 | Defined in Clause 11.4.4
182 | MCO | ? | 8.7 |  |  |  | Assoc | How does the coordinator determine if a station is still present in the network? | Any device can send any directed command frame to any other device to see if it is present. Add to peer discovery clause. | Add to peer discovery clause | A | C |  |  | Gubbi | Done in D05
186 | WMS | 4 | 7.2.1.1.3 | 59 | 10 | t | Frame Type | Folding commands into frame types requires using 6 bits to the Frame Type Field | Change text to "The frame type field is six bits in length." | Change frame formats to ammendments adopted in 01/298r0 | A | C |  |  | Gubbi | Done in D06
192 | WMS | 4 | 7.5.2 | 77 |  |  | Cmd Types | Probe Information, Channel Status Request, Device information commands should be request/response or request/indication frames | Change to request and response or indication. see doc:01/259r0 for text detail and change to frame format. Raju included Channel Status Request and response, Device Information request and response in 01292r1table 42. Probe information still does not have request and response. | Raju should add Probe information Request and Probe information response. | A | C |  |  | Gubbi | Done in D06
198 | WMS | 4 | 7.5.1.1 | 75 |  |  | Channel Time Request | Need to add destination station address to Channel Time Request. | WMS to supply text to describe new Channel time request message structure. Note Raju changed Channel Time Request to use stream Index in 01292r1. | WMS to provide additional detail in doc: 01/259r0 | A | C |  |  | Gubbi | Done in D05
205 | WMS | 4 | 7.3.4 | 64 | 12-32 |  | CoordSel | Modify Coordinator Selection frame Body to reflect new coordinator criteria | In figure 6 remove total external connections, active external connections, total system memory, available system memory, Maximum PHY transmit power, Maximum PHY rate. Add Battery/AC power, designated coordinator bit, MAX GTS slots, Repeater memory, Max Repeater Rate. Review with Raju | WMS to provide additional detail in doc: 01/259r0 | A | C |  |  | Gilb | Done in D07
206 | WMS | 4 | 7.3.4 |  |  | T | CoordSel | Modify Comparison order of fields in the AC announcement frame | WMS to supply text Review with Raju. | WMS to provide additional detail in doc: 01/259r0 | A | C |  |  | Gubbi | Pending | Amendment approval
208 | WMS | 4 | 8.3 |  |  |  | TSF |  | WMS needs to identify the WMS to supply detailed timing diagram to show the position of time zero in the superframe | WMS to supply details in 01259rx | A | C |  |  | Shvodian | Done in D06
209 | WMS | 4 | 7.4.2 | 72 | 8 |  | TSF | Replace the TSF field with beacon number | Remove 8 byte Time Stamp field and replace with 4 byte Beacon Number field | WMS to supply details in 01259rx | A | C |  |  | Shvodian | Done in D06
210 | WMS | 4 | 7.3.2 | 64 | 17 |  | TSF | Replace the TSF field with beacon number | Change "TSF Element" to "Beacon Number". Add number of bits to 01259 | WMS to supply details in 01259rx | A | C |  |  | Shvodian | Done in D06
211 | WMS | 4 | 8.1.4 | 88 |  |  | Assoc | Broadcast the device information table when a station associates | WMS to supply modified text for section 8.1.4 | WMS to provide detail in doc: 01/259r0 | D | C |  |  | Shvodian | Done in D06, 8.2.9 | Amendment Approval
212 | WMS | 4 | 8.1.5 | 89 |  |  | Disassociation | Broadcast the device inforamtion table when a station disassociates | WMS to supply modified text for section 8.1.5 | WMS to provide detail in doc: 01/259r0 | D | C |  |  | Shvodian | Done in D06 | Amendment Approval
213 | WMS | 4 | 7.4.3 | 72 | 43-48 |  | Capability | Add MAX GTS slots to the capability field. This puts a limit on how many GTS slots can be assigned to a station. This is the combined number of source and destiantion slots for the station | Add 8 bit MAX GTS slot field to the capability field. Change reserved bits to 3 reserved bits. | WMS to provide detail in doc: 01/259r0. | A | C |  |  | Shvodian | Done in D05 | Additional Parms defined in Amendment Doc 355
214 | WMS | 4 | 7.3.3 | 64 | 34-36 | T | Ack | Stream index and sequence control fields are not needed for immediate Acks. | Remove this sentence, and add stream index and sequence control to lines 28 and 29 so that these fields are unused and set to zero. | Remove this sentence, and add stream index and sequence control to lines 28 and 29 so that these fields are unused and set to zero. | A | C |  |  | Gubbi | Done in D05 | 7.3.2
215 | WMS | 4 | 7.5.1.1 | 76 | 9-14 | T | Priorities | Are 3 priorities of asynchronous traffic really needed? | Need to look at 802.1D | These priorities were removed in D06 | D | C |  |  | Heberling | Done in D06 | Amendment Approval
216 | WMS | 4 | 8.4.1 | 94 |  | T | Stream Mgt | Why is the coordinator in the loop for stream negotiation? Stream negotiation does not address channel time requests. | Remove the coordinator from stream negotiation. Have stream index be unique for a SA/DA pair. | Reduce the stream index to 8 bits with the remaining 3 bits reserved. So this results in simpler implementation based on global stream index that is allocated by PNC. An implementation based stream index that is unique for SA/DA pair results in more complex implementation. Add Stream-index to ChnlTimeReq by replacing reserved field in Fig.22, Clause 7.5.1.1; Add Stream-index to ChnlTimeAllocationBlock alog with one reserved byte in figure 20 clause 7.4.9; Remove time slot duration from CTA block in Fig. 20, clause 7.4.9; Add ChnlTimeReq Block to Stream QoS parms in Stream Mgt . Cmnd in figure 42 Clause 7.5.12; Retain StreamID in Stream QoS parms.; Add descriptions for each of the "new" fields. | X | C |  |  |  | Done in D06 | Add text in col K to doc: 355. Approval of Amendments
217 | WMS | 4 | 7.5.1.1 | 76 |  | t | Channel time | A)How long is a channel time request good for? Until the next one? B)What happens if the PNC allocates less channel time than what was allocated? Does it allocate more if it becomes available? |  | A is addressed in Amendment Doc: 355. B)What happens if the PNC allocates less channel time than what was allocated? Does it allocate more if it becomes available? Yes. Add clarification in 8.2.3.2 | X | C |  |  | Gilb | Done in D06 | Approval of Amendments
219 | WMS | 4 | 8.2.3.1 | 92 | 14-15 | T | CAP | Resolution (quantzation) of the random backoff timer needs to be specified. | Bill will provide resolution recommendation in 01259 |  | D | C |  |  | Shvodian | Done in D06, 8.3.2.1 | Amendment Approval
220 | WMS | 4 | 8.1.3 | 87 | 1-54 | E | CoordSel | This section refers to the CS-Frames being transmitted. The action (AC announcement, AC pullout, New Coord. Announcement) should be spelled out for clarity. | Make specifiic references to the action type of the each CS-Frame. | Make specifiic references to the action type of the each CS-Frame. | A | C |  |  | Gubbi | Done in D05 | 8.1.3
225 | Vienna | 4 | 8.1.7 | 89 |  | E | DevReg | Better definition of registration is needed | Add text based on Raju's e-mail of 6/18/01and verify that it fits with the security clause. PNID should always have the PNID that appears in the Beacon. Open registration should be accomplished through a new open registration command (if needed) and not via a null PNID. | Add text based on Raju's e-mail of 6/18/01and verify that it fits with the security clause. PNID should always have the PNID that appears in the Beacon. Open registration should be accomplished through a new open registration command (if needed) and not via a null PNID. | A | C |  |  | Gilb | Done in D07 | Ammendment approval
226 | MKS | 4 |  |  |  | T | Stream Mgt | Look at merging channel time requests and stream management |  |  |  | C |  |  | Gilb | Done | see item 216
227 | Vienna | 4 | 6 | 17 | 19 | T | SME | Remove the top of the SME box to indicate that an undefined interfaceto the SME exists a la 802.11. |  | Remove the top of the SME box to indicate that an undefined interfaceto the SME exists a la 802.11. | A | C |  |  | Roberts | Done in D05
228 | Vienna | 4 | 7.1.2 | 48 | 7 | T | Frame Body | Max Frame body size is inconsistent between section 7.1.2 and section 11.2.7 |  | MAX Frame parameter is Phy dependent parameter that is used in both MAC and PHY clauses. | D | C |  |  | Gubbi/Gilb | Done in D06
231 | Vienna | 4 | 6.5 | 39 |  | T | CoordSel | Need to add the Des-mode bit into the MAC PIB | Add MACPIBPNCDesMode to the MAC PIB. | Add MACPIBPNCDesMode to the MAC PIB. | A | C |  |  | Roberts | Done in D06 | Amendment approval
232 | Vienna | 4 | 7 and 8 |  |  | T | CoordSel | Do a global change of Des-Mode to PNC-Des-Mode in Clause 7 and 8. | Do a global change of Des-Mode to PNC-Des-Mode in Clause 7 and 8. | Do a global change of Des-Mode to PNC-Des-Mode in Clause 7 and 8. | A | C |  |  | Gubbi | Done in D05
237 | Vienna | 4 |  |  |  | T | TxPwr | How is the Tx Power control managed and reported to the SME for each destination (does it need to be in the PIB?) |  | SME doesn't need to know this, the MAC keeps the information internal to itself. | D | C |  |  | Roberts/Bain | Rejected | Pending results of further study.
238 | Vienna | 4 |  |  |  | T | Immediate ACK | How often does a DEV retry Immediate ACK frames? | Retry limit is in stream negotiation. What about non-stream? |  | X | C |  |  |  | Done in D05
239 | Vienna | 01292r1 | 7.5 | 69 | Table 42 | T | Cmd Types | Repeater service Reject and Repeater Service Grant should be Repeater Service Response, Sleep state Permit and Reject should be consolidated to Response. |  | A)Repeater service Reject and Repeater Service Grant should be Repeater Service Response, B)Sleep state Permit and Reject should be consolidated to Response. | A | C |  |  | Gubbi | Done in D05 | A withdrawn, B adopted.
240 | James | 6 | 8.2.7 | 99 |  | T | DevReg | Registration is a higher layer function. | Delete reference to registration in D07, i.e. delete 8.2.7. |  | A | C |  |  | Gilb | Done in D07
362 | WMS | 6 | 8.7.3 | 109 | 27 | T | ACK Policy | Why is delayed ACK not allowed for broadcast or multicast frames? | Allow delayed ACK for broadcast or multicast frames. |  | A | Z
304 | ADH | 6 | 7.5.17 | 91 | 45 | E | ACK | The ACK policy field definition is TBD | Please provide definition |  | A | C |  |  | Gilb | Due D08
289 | ADH | 6 | 7.5.9 | 86 | 10-12 | T | Channel Status Response | Length = 0 If it is zero why have it. | Get rid of the length field in the CSR frame. | T/L/V encoding Type/Length/Value | X | Z