IEEE P802.15

Wireless Personal Area Networks

| Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs) |
| --- | --- |
| Title | AltPHY Study Group Draft Schedule Proposal |
| Date Submitted | 20 Dec 2001 |
| Source | [Rick Roberts] [XtremeSpectrum, Inc.] [8133 Leesburg Pike, Suite 700 Vienna, Va. 22182 | Voice: [ 703.269.3043 ] Fax: [ 703.749.0248 ] E-mail: [ rroberts@xtremespectrum.com ] |
| Re: |  |
| Abstract | This document presents a draft of an Alternate PHY study group schedule for consideration by the group. |
| Purpose |  |
| Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein. |
| Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15. |

Proposed IEEE802.15.3a Key Events

| November | Approve 15.3a Study Group |
| --- | --- |
| December | Issue CFA (applications) |
| January (Interim) | Application Presentations |
| March (Plenary) | Application Presentations Work on Requirements followed by Selection Criteria Generate Application Summary (note: all aspiring 15.3a voters need to start attendance at this meeting – the MAY meeting is in Australia and if not attending that meeting then start attendance in January) |
| May (Interim) | Approve Requirements document Approve Selection Criteria Issue CFP (proposals) Approval of PAR and 5 Criteria by WG |
| July (Plenary) | Proposal Presentations Proposal evaluation against selection criteria Approval of PAR by ExCom |
| September (Interim) | Proposal Selection Voting Generation and acceptance of baseline draft text |
| November (Plenary) | Presentation and approval of Alt PHY draft text Approval to conduct a letter ballot |

Detail for Proposed Schedule

  - Approve 15.3a in Austin (November meeting) and shortly thereafter issue a Call for Applications.

  - Conference calls between Austin and January meeting to work on CFA.

  - At January meeting, present application papers.

  - Conduct conference calls between January and March to start work on requirements and then the selection criteria.

  - March meeting – Continue application presentations.  Work on requirements followed by work on the selection criteria.  Summarize application presentations.

  - Between March and May - Continue work on requirements document and selection criteria.  Work on CFP.  Work on PAR and 5 Criteria.

  - May meeting … Approve requirements document, approve selection criteria and issue CFP.  Finish PAR and 5 Criteria for WG presentation and approval.

  - Between the May and July meetings, start reviewing proposals and start proposal evaluations.

  - Submit PAR and 5 Criteria to ExCom by June 7th to make 30 day notice requirement.

  - At the July meeting – proposal presentations and proposal evaluation against selection criteria.   Approval of PAR and 5 Criteria by ExCom.

  - Between July and September meetings, continue proposal review and evaluation.

  - September meeting … conduct proposal selection voting and generation/acceptance of baseline draft text.

- Between the September and November meetings – Text Drafting

November meeting – presentation and approval of the draft text. Approval to conduct a letter ballot.

# Text boxes

Project Timeline

Study Group 3a - Alt Phy SG