## TBD count
clause | subject | TBD
28 |  | 3
44 |  | 2
45 |  | 4
55.3 | PCS | 28
55.4 | PMA | 22
55.5 | pmaelec | 38
55.6 | management | 14
55.7 | Link Segment
55.8 | MDI | 1
55.11 | Delay | 3
55.12 | PICS | 22
Total |  | 137

## 55.3 PCS
55.3 PCS
| Description | page | From line | to line | Num TBDs | Suggested action
6 | PCS Scrambler | 163 | 1 | 2 | 2 | Make initial seeds implementer's choice
12 | Test Pattern generators | 165 | 8 | 60 | 9 | Need proposals.
16 | PMA Training | 167 | 22 | 23 | 2 | Repetition period for training and InfoFields must be defined. Dependent on # of THPs & size of CRC. Drives Start-up
16.2 | InfoField Definition | 169 | 8 | 17 | 12 | InfoField bits driven by THP settings and start-up; need proposals
16.3 | Decoding of subgroups | 169 | 21 | 22 | 1 | From 1G draft; should be eliminated
18.2 | Error block counter | 173 | 39 | 40 | 1 | Need # of bits; recommend 6
18.3 | Loopback MDIO register | 174 | 52 | 53 | 1 | Should be defined; Mike McConnell?
0 | Additional MDIO registers |  |  |  |  | More registers may be need for additional items being defined
Total TBDs
28

## 55.4 PMA
55.4 PMA
| Description | page | From line | to line | Num TBDs | Suggested action
2.4 | PHY control function (start-up procedure) | 179 | 14 | 39 | 1 | PHY control defines the start-up sequence. Draft 1.3 has a baseline start-up that requires more details from THP and Power Backoff settings and timers for each state
3.1 | THP details | 180 | 34 | 44 | 8 | Draft comprimise THP proposal failed in Jan. Need detailed coef sets for at least 3 IIRs and 3 FIRs (short, medium, long) plus bypass
5.2 | Timers | 182 | 41 | 11 | 12 | These timers control the dwell time of state diagrams. Several TBDs from start-up
6.2 | Reference to Autoneg | 185 | 31 | 31 | 1 | Confirm with Eric Lynskey
Total TBDs
22

## 55.5 PMA Electrical
0 | PMA ELECTRICALS
| Description | page | From line | to line | Num TBD | Suggested action
1 | Isolation requirement | 187 | 10 | 25 | 1 | Review and approve text
2 | Test channel for tx jitter tests | 188 | 4 | 16 | 10 | Table 55-2: 9 TBDs. Provide length of sections, impedance of non-50ohm segments & their insertion loss; proposal needed on the jitter test channel
3 | Control register bits for test modes | 188 | 28 | 29 | 3 | TBD bits for 10GBASE-T control Register; Recommend: ??Eric, ??Mike
3 | Number of symbols for voltage tests | 189 | 1 |  | 1 | TBDnumsym: number of symbols for voltage test: Recommend 10; corresponds to 40MHz
3 | Frequencies for single tone tests | 189 | 19 | 29 | 4 | Suggest frequencies as multiples of 800/1024: Two proposals: (53, 101, 167) and (13, 23, 53, 101,167). Need decision
3 | Frequencies for single two tone tests | 189 | 19 | 29 | 3 | Suggest frequency pairs as multiples of 800/1024:proposal [179,181], [277,281], [397,401]; need task force approval
3 | Test setup for tx jitter measurements | 192 | 1 | 23 |  | Approve figure 55-24; could modify caption to say "or equivalent"
4 | Transmit voltage peak to peak | 192 | 42 | 42 | 1 | Pick number between 2 & 2.5V: recommend 2V
4 | Transmit voltage peak to peak tolerance | 192 | 42 | 42 | 1 | Specify % tolerance of +-15% or less; with 2V this covers 1.7V to 2.3V; power spec will impose additional constraint
5 | Transmitter linearity: value of TBDXnonlin | 193 | 18 | 20 | 1 | Value of TBDXnonlin
5 | Transmitter linearity: value of TBDXnlslope | 193 | 18 | 20 | 1 | Value of TBDNLslope;
5 | Fo | 193 | 18 |  | 1 | Lower end of freq range. Set F0 to 5MHz
5 | F1 | 193 | 18 | 20 | 1 | breakpoint of linearity roll off requirement; has to be set in concert with Xnonlin to avoid a discontinuous spec;log10(F1)=(89-Xnonlin)/20
5 | Recommended linearity | 193 | 37 | 37 | 2 | Provide values of Nonlinearity & slope for recommended requirements
6 | Jitter specification | 193 | 49 | 55 | 6 | Jitter has three impacts: i) Transmit waveform distortion ii) Distortion in slave transmitter due to jitter in the master transmitter iii) Echo cancellation floor at receiver; Recommendation: Cover (i) by specifying an SNDR test in master mode; cover (ii) by specifying an SNDR test in slave mode; cover (iii) by receiver test in 55.5.9; detailed proposals/specs needed
10 | Common mode noise tolerance | 195 | 25 | 40 | 2 | Pick max p-to-p common mode voltage receiver must be able to tolerate; as written, allows for higher tolerance requirement at lower frequency; specify breakpoint in freq.
Total TBDs
38

## 55.8 MDI
0 | MDI
| Description | page | From line | to line | num TBD | Suggested action
3 | TBD in tolerance of cable impedance | 214 | 36 | 37 | 1 | The differential impedance at the MDI for each transmit/receive channel shall be such that any reflection due to differential signals incident upon the MDI from a balanced cabling having an impedance of 100 ohm ±TBD% is attenuated, relative to the incident signal, at least 16 dB ...; recommend +-10%
Total TBD
1